摘 要
本計畫範圍為臺中市山坡地範圍內各集水區合計55,328公頃，主要包含56個子集水區。因近年來強降雨、長延時事件頻仍，災害逐漸趨向複合型，為利於掌握轄區內各子集水區後續經營主軸，特針對臺中市境內各山坡地集水區進行調查規劃之檢討評估，並擬定集水區調查規劃之分年分期計畫，以期達到災害基本控制、集水區經營目的及集水區保育(水土林動人)等多贏的目標。
根據計畫目標，本計畫之集水區治理需求級序評估方式如下：
(一) 蒐集彙整歷年集水區調查規劃報告，做為瞭解集水區歷史災害及治理情形之背景資料，並參考水土保持局整體性治山防災計畫中之集水區土砂災害潛勢評估指標進行初步評估分析，做為集水區土砂災害潛勢背景資料。
(二) 依據集水區背景資料進行現況調查，調查重點包括各集水區內土石流防災專員訪談之可能致災點位、地方治理需求之工程點位、治山防災構造物、歷次颱風新增災害等，以評估集水區內優先處理、需要處理及暫緩處理之治理需求。
(三) 在現階段「安全」經營主軸之下，根據集水區內優先處理、需要處理及暫緩處理之治理需求評估集水區有無立即危險與治理之急迫性，集水區現況問題若屬於優先處理者，列為治理需求級序較高之集水區，經營重點為土砂災害防治；並根據集水區構造物總體檢及分年分期治理計畫落實情形之調查結果，評估集水區之治理成效與構造物受損情形，以做為治理需求評定依據，針對需要處理及暫緩處理之災害問題，進行處理及加強觀察，針對構造物毀損則進行加強及改善，經營重點為區域性水土資源保育；而根據調查結果集水區環境已具備良好之安全基礎，現況暫無災害治理需求者，集水區經營重點即以農村發展為主，可針對集水區內有具發展潛力之農村社區，進一步結合水土保持與農村再生，達到集水區水土資源永續經營之目標。
(四) 綜合上述各項評估過程，則可得到各集水區之治理需求級序。
根據上述原則評估得到各集水區之治理需求級序後，即可依據其治理需求級序編列集水區之分年分期計畫。集水區治理需求評估執行架構如圖1所示。

圖1 集水區治理需求評估執行架構
根據蒐集歷年規劃報告成果，臺中市山坡地轄區範圍自90～100年開始辦理整體規劃統計共34件，其中規劃案以各子集水區為單元進行治理調查規劃工作共28件，可提供做為各子集水區現況調查之基礎背景資料；現況調查重點包括土石流防災專員訪談之可能致災點位、地方治理需求之工程點位、治山防災構造物之現況調查和歷次颱風新增災害檢視彙整，藉由災害與治理情形之現勘結果，評估集水區現況是否穩定，經調查現況具有災害之區位共計145處，可分為優先處理、需要處理及暫緩處理等3種災害類型；根據集水區構造物總體檢結果，則完成200件治山防災構造物之調查，統計歷年來臺中市山坡地範圍主要之治理工程內容，多以護岸、擋土牆、固床工及排水溝為主，根據構造物現況功能性之分析統計結果，經評估功能性為A級者有155件、B級計28件、C級計17件，總件數共計200件，總受損件數共計45件。針對各構造物受損情形，亦提出詳細之修復對策及修復經費。
集水區經營主軸可分為「安全、傳承、永續」等三階段目標，現階段為保護集水區內保全對象之生命財產安全、避免土砂災害之威脅，應以集水區土砂災害之治理為首要，因此，針對山坡地子集水區之經營與治理部分，不論是為了避免災害發生或利於產業之發展，現階段之山坡地集水區經營主軸皆以「安全」為優先。
在「安全」經營主軸之下，為掌握臺中市山坡地各子集水區後續經營治理之特性，依據現勘結果，經評估集水區內治理需求屬於優先處理者，經營重點為「土砂災害防治」，需要處理及暫緩處理者，經營重點為「區域性水土資源保育」，現況無明顯災害治理需求，已可提供農村發展所需之良好集水區環境者，集水區經營重點則為「農村發展」，依據各山坡地子集水區不同之經營重點，做為爾後集水區經營工作參考。
本計畫根據治理需求評估各山坡地子集水區之經營重點，在現階段安全之經營主軸下，提出臺中市山坡地集水區經營重點評估結果如表1。首先，包含頭汴坑溪、草湖溪及龍井子集水區等26個子集水區，現況皆有可能對保全對象造成較立即性影響之土砂災害問題，經營重點為「土砂災害防治」，應積極落實集水區內易致災潛勢地區之治理與防災工作。其次，在大安溪下游等10個子集水區，現況雖無立即之土砂災害威脅，但可能有擴大之虞而間接影響保全對象，現況問題多屬於需要處理，集水區經歷年治理目前已逐漸恢復穩定，後續應針對治理需求進行改善，以延續治理成效，集水區經營重點主要為「區域性水土資源保育」，後續經營治理應以強化集水區水土資源保育為重點，包含安全排水、農地水土保持、構造物修復等，以進一步加強集水區水土資源之保育。最後包含四季郎溪等20個子集水區，現況並無明顯之土砂災害治理需求，集水區坡地狀況已大致恢復穩定，在此安全的基礎下，可提供農村發展所需之良好集水區環境，集水區經營重點主要為「農村發展」，後續針對集水區內具發展潛力之農村社區，應加強結合水土保持及農村再生，以達到集水區水土資源永續經營之目標。
本計畫以經營重點屬於土砂災害防治之子集水區為主，依據治理需求級序之優先順序與調查規劃需求性，同時考量歷年集水區調查規劃之檢討結果，編列臺中市山坡地集水區調查規劃之分年分期計畫如表2。

表1 臺中市山坡地集水區治理需求級序及經營重點評估表
項次	子集水區	子集水區 / 編號	現況調查評估(件)				經營重點	治理需求 / 級序
			優先處理	需要處理	暫緩處理	合計
1	頭汴坑溪	1104006	24	2	11	37	土砂災害防治	1
2	草湖溪	1104007	10	11	5	26	土砂災害防治	2
3	大甲溪中游	1004015	9	8	1	18	土砂災害防治	3
4	石角溪	1004016	5	5	1	11	土砂災害防治	4
5	大坑溪	1104004	4	─	─	4	土砂災害防治	5
6	廓子溪	1104005	3	3	1	7	土砂災害防治	6
7	龍井	3201003	3	2	─	5	土砂災害防治	7
8	乾溪	1104008	3	1	4	8	土砂災害防治	8
9	中坑港	1104001	3	1	─	4	土砂災害防治	9
10	葫蘆墩圳	1005001	2	7	─	9	土砂災害防治	10
11	大甲溪下游	1005002	2	4	─	6	土砂災害防治	11
12	梨山	1001039	2	2	─	4	土砂災害防治	12
13	佳陽社區	1001041	2	2	─	4	土砂災害防治	13
14	沙鹿	3201002	2	─	1	3	土砂災害防治	14
15	南湖溪下游	1001025	2	─	─	2	土砂災害防治	15
16	環山	1001026	1	2	─	3	土砂災害防治	16
17	清泉橋	1001037	1	2	─	3	土砂災害防治	17
18	中嵙溪	1004017	1	1	2	4	土砂災害防治	18
19	佳陽	1001043	1	1	─	2	土砂災害防治	19
20	蟾蜍石	901033	1	1	─	2	土砂災害防治	20
21	筏子溪	1103001	1	1	─	2	土砂災害防治	21
22	雪山坑溪	901039	1	─	─	1	土砂災害防治	22
23	沙蓮溪	1004011	1	─	─	1	土砂災害防治	23
24	白毛	1004013	1	─	─	1	土砂災害防治	24
25	二櫃溪	1101034	1	─	─	1	土砂災害防治	25
26	清水	3201001	1	─	─	1	土砂災害防治	26
27	和平	1004014	─	2	2	4	區域性水土資源保育	27
28	烏牛欄溪	1104002	─	2	2	4	區域性水土資源保育	28
29	七家灣溪	1001015	─	2	─	2	區域性水土資源保育	29
30	大里溪	1104010	─	2	─	2	區域性水土資源保育	30

資料來源：本計畫製作
表1 臺中市山坡地集水區治理需求級序及經營重點評估表(續)
項次	子集水區	子集水區 / 編號	現況調查評估(件)				經營重點	治理需求 / 級序
			優先處理	需要處理	暫緩處理	合計
31	烏石坑溪	901043	─	2	─	2	區域性水土資源保育	31
32	大安溪下游	901022	─	1	─	1	區域性水土資源保育	32
33	觀音坑	901046	─	1	─	1	區域性水土資源保育	33
34	中冷	1004009	─	1	─	1	區域性水土資源保育	34
35	旱溪	1104003	─	─	3	3	區域性水土資源保育	35
36	象鼻坑	1106005	─	─	1	1	區域性水土資源保育	36
37	四季郎溪	1001017	─	─	─	0	農村發展	37
38	茶岩山	1001027	─	─	─	0	農村發展	38
39	東捫岡	1001036	─	─	─	0	農村發展	39
40	武加加南山	1001038	─	─	─	0	農村發展	40
41	德基水庫	1001044	─	─	─	0	農村發展	41
42	谷關	1003006	─	─	─	0	農村發展	42
43	稍來溪	1003007	─	─	─	0	農村發展	43
44	佳保臺	1004004	─	─	─	0	農村發展	44
45	十文溪	1004005	─	─	─	0	農村發展	45
46	松鶴	1004006	─	─	─	0	農村發展	46
47	唐馬山東側	1004007	─	─	─	0	農村發展	47
48	理冷溪	1004008	─	─	─	0	農村發展	48
49	東卯溪	1004010	─	─	─	0	農村發展	49
50	橫流溪	1004012	─	─	─	0	農村發展	50
51	石岡	1004018	─	─	─	0	農村發展	51
52	大甲	1006001	─	─	─	0	農村發展	52
53	包安溪	1101030	─	─	─	0	農村發展	53
54	牛坪坑	1101031	─	─	─	0	農村發展	54
55	大竹	1106008	─	─	─	0	農村發展	55
56	烏溪下游	1106009	─	─	─	0	農村發展	56

資料來源：本計畫製作

表2 臺中市山坡地集水區調查規劃分年分期計畫
項次	子集水區	子集水區編號	經營階段	治理需求 / 級序	分年分期 / 順序	備註
1	頭汴坑溪	1104006	土砂災害防治	1	第一期	--
2	草湖溪	1104007	土砂災害防治	2	第一期	--
3	大甲溪中游	1004015	土砂災害防治	3	第一期	--
4	石角溪	1004016	土砂災害防治	4	第二期	--
5	大坑溪	1104004	土砂災害防治	5	第二期	--
6	廓子溪	1104005	土砂災害防治	6	第二期	--
7	龍井	3201003	土砂災害防治	7	--	100年已規劃
8	乾溪	1104008	土砂災害防治	8	第三期	--
9	中坑港	1104001	土砂災害防治	9	第三期	--
10	葫蘆墩圳	1005001	土砂災害防治	10	--	100年已規劃
11	大甲溪下游	1005002	土砂災害防治	11	--	100年已規劃
12	梨山	1001039	土砂災害防治	12	--	101年規劃中
13	佳陽社區	1001041	土砂災害防治	13	--	101年規劃中
14	沙鹿	3201002	土砂災害防治	14	--	100年已規劃
15	南湖溪下游	1001025	土砂災害防治	15	--	101年規劃中
16	環山	1001026	土砂災害防治	16	--	101年規劃中
17	清泉橋	1001037	土砂災害防治	17	--	101年規劃中
18	中嵙溪	1004017	土砂災害防治	18	第四期	--
19	佳陽	1001043	土砂災害防治	19	--	101年規劃中
20	蟾蜍石	901033	土砂災害防治	20	第四期	--
21	筏子溪	1103001	土砂災害防治	21	第四期	--
22	雪山坑溪	901039	土砂災害防治	22	第四期	--
23	沙蓮溪	1004011	土砂災害防治	23	第四期	--
24	白毛	1004013	土砂災害防治	24	第四期	--
25	二櫃溪	1101034	土砂災害防治	25	第四期	--
26	清水	3201001	土砂災害防治	26	--	100年已規劃

*註：預定執行期程以每期為2~3年度辦理，實際執行期程仍須依照水土保持局臺中分局經費及需求辦理。
資料來源：本計畫統計整理
Abstract
The scope of this project comprises of all watersheds of slopeland in Taichung City with total are of 55,328 hectares. Primarily they include 56 sub-watersheds. Due to frequent heavy rainfalls and time-lapse rainfall events in recent years, the disasters gradually tend to be compound in nature. Therefore in order to have a good command of the ensuing operational theme for all sub-watersheds within jurisdiction, we specifically proceeded to review and assess all slopeland watersheds within Taichung City. In addition, we also planned the annual and phased-in surveys in the watersheds with the expectation to reach Win-Win objectives in the disaster basic control, watersheds operations and conservations (enchanting water, soil and forest).
According to the 2001~2011 processed integration survey planning report, 30 items had been implemented and these can serve as the foundation background information for each current sub-watershed status survey. There are a total of 45 currently surveyed disaster regions which can be broken down into 3 types of disasters with classes of top-priority, needed to process and on-hold. There are 200 items completed in the category of mountain governance and disaster prevention structure surveys. After they are assessed for functionalities and there are 155 Class-A, 28 Class-B and 17 Class-C and a total of 200 cases in addition to 145 damaged items which targeted to the level of damage for each structure.
The operation themes for watershed can be separated into three-staged objectives: “Safety, heritage and sustainability” for the purpose of protecting the lives and property safeties and threat prevention from sediment disaster for the protected subjects within watershed. And the operation theme at the current phase is prioritized as “Safety”.
Under the pretext of “safety” operation, in order to control the aftermath operation and governance characteristics for each sub-watershed at slopeland within Taichung City, and guided by survey findings and the governance requirements assessed as high-priority within watershed area, the operation will focus on “Sediment disaster prevention”. For those required governance and put on-hold, the operation will focus on “Regional land and water resources conservation”. For those currently without significant disaster governance demand, they can provide and serve as the good watershed environment needed by rural development. The essential for watershed operation rests at “Rural development”. And according to different operation focuses for sub-watersheds at each slopeland, these can serve as references intended for watershed operation personnel.
Findings from the appraisals indicate that, first of all, 26 sub-watersheds at Tou-Bian-Kun Creek, Grass Lake Creek and Lung-Jin-Tze watershed, etc, the operation focus is “Sediment disaster prevention” and the governance and disaster prevention tasks for watershed that have disaster-prone potentials should be implemented as such. Other than these, 10 sub-watersheds at the downstream of Da-An Creek, etc, the operation focus should be “Regional land and water resources conservation”. The aftermath operation and governance should strengthen the soil and water conservation at watershed as the theme, including safety drainage, farm land water and soil conservation and structure repair, etc, so as to further strengthen the water and soil conservation at watershed. Lastly, 20 sub-watersheds at Si-Chi-Lun Creek, etc, the operation focus should be “Rural development”. And the aftermath tasks should strengthen the integration between water and soil conservation and rural rejuvenation for those rural communities with development potentials within the watershed so as to reach the objective of sustainable operation for water and soil resources in watershed.