摘 要
本計畫範圍為苗栗縣境內山坡地範圍，山坡地面積約89,611公頃，主要涵蓋28個山坡地子集水區，集水區面積約150,202公頃。因近年來強降雨、長延時事件頻仍，災害逐漸趨向複合型，為利於掌握轄區內各子集水區後續經營主軸，特針對苗栗縣境內各山坡地集水區進行調查規劃之檢討評估，並擬定集水區調查規劃之分年分期計畫，以期達到災害基本控制、集水區經營目的及集水區保育(水土林動人)等多贏的目標。
根據計畫目標，本計畫之集水區治理需求級序評估方式如下：
(一) 蒐集彙整歷年集水區調查規劃報告，做為瞭解集水區歷史災害及治理情形之背景資料，並參考水土保持局整體性治山防災計畫中之集水區土砂災害潛勢評估指標進行初步評估分析，做為集水區土砂災害潛勢背景資料。
(二) 依據集水區背景資料進行現況調查，調查重點包括各集水區內土石流防災專員訪談之可能致災點位、地方治理需求之工程點位、治山防災構造物、歷次颱風新增災害等，以評估集水區內優先處理、需要處理及暫緩處理之治理需求。
(三) 在現階段「安全」經營主軸之下，根據集水區內優先處理、需要處理及暫緩處理之治理需求評估集水區有無立即危險與治理之急迫性，集水區現況問題若屬於優先處理者，列為治理需求級序較高之集水區，經營重點為土砂災害防治；並根據集水區構造物總體檢及分年分期治理計畫落實情形之調查結果，評估集水區之治理成效與構造物受損情形，以做為治理需求評定依據，針對需要處理及暫緩處理之災害問題，進行處理及加強觀察，針對構造物毀損則進行加強及改善，經營重點為區域性水土資源保育；而根據調查結果集水區環境已具備良好之安全基礎，現況暫無災害治理需求者，集水區經營重點即以農村發展為主，可針對集水區內有具發展潛力之農村社區，進一步結合水土保持與農村再生，達到集水區水土資源永續經營之目標。
(四) 綜合上述各項評估過程，則可得到各集水區之治理需求級序。
根據上述原則評估得到各集水區之治理需求級序後，即可依據其治理需求級序編列集水區調查規劃之分年分期計畫。集水區治理需求評估執行架構如圖1所示。

圖1 集水區治理需求評估執行架構
根據蒐集歷年集水區調查規劃報告成果，苗栗縣山坡地轄區範圍自90～100年開始辦理調查規劃，共計已執行22件調查規劃工作，可提供做為各子集水區現況調查之基礎背景資料；現況調查重點包括土石流防災專員訪談之可能致災點位、.地方治理需求之工程點位、治山防災構造物之現況調查和歷次颱風新增災害檢視彙整，藉由災害與治理情形之現勘結果，評估集水區現況是否穩定，經調查現況具有災害之區位共計125處，可分為優先處理、需要處理及暫緩處理等3種災害類型；根據集水區構造物總體檢結果，則完成202件治山防災構造物之調查，統計歷年來苗栗縣山坡地範圍主要之治理工程內容，多以護岸、擋土牆、固床工及排水溝為主，經評估其功能性為A級者169件、B級30件、C級3件，受損件數共計33件，針對各構造物受損情形，亦提出詳細之修復對策及修復經費。
集水區經營主軸可分為「安全、傳承、永續」等三階段目標，現階段為保護集水區內保全對象之生命財產安全、避免土砂災害之威脅，應以集水區土砂災害之治理為首要，因此，針對山坡地子集水區之經營與治理部分，不論是為了避免災害發生或利於產業之發展，現階段之山坡地集水區經營主軸皆以「安全」為優先。
在「安全」經營主軸之下，為掌握苗栗縣山坡地各子集水區後續經營治理之特性，依據現勘結果，經評估集水區內治理需求屬於優先處理者，經營重點為「土砂災害防治」，需要處理及暫緩處理者，經營重點為「區域性水土資源保育」，現況無明顯災害治理需求，已可提供農村發展所需之良好集水區環境者，集水區經營重點則為「農村發展」，依據各山坡地子集水區不同之經營重點，做為爾後集水區經營之重點工作參考。
本計畫根據治理需求評估各山坡地子集水區之經營重點，在現階段安全之經營主軸下，提出苗栗縣山坡地集水區經營重點評估結果如表1。首先，包含景山溪等21個子集水區，集水區現況皆有可能對保全對象造成較立即性影響之土砂災害問題，經營重點為「土砂災害防治」，應積極落實集水區內易致災潛勢地區之治理與防災工作。其次，在北坑溪等3個子集水區，集水區現況雖無立即之土砂災害威脅，但可能有擴大之虞而間接影響保全對象，現況問題多屬於需要處理，集水區經歷年治理目前已逐漸恢復穩定，後續應針對治理需求進行改善，以延續治理成效，集水區經營重點主要為「區域性水土資源保育」，後續經營治理應以強化集水區水土資源保育為重點，包含安全排水、農地水土保持、構造物修復等，以進一步加強集水區水土資源之保育。最後包含天狗等4個子集水區，現況並無明顯之土砂災害治理需求，集水區坡地狀況已大致恢復穩定，在此安全的基礎下，可提供農村發展所需之良好集水區環境，集水區經營重點主要為「農村發展」，後續針對集水區內具發展潛力之農村社區，應加強結合水土保持及農村再生，以達到集水區水土資源永續經營之目標。
本計畫以經營重點屬於土砂災害防治之子集水區為主，依據治理需求級序之優先順序與調查規劃需求性，同時考量歷年集水區調查規劃之檢討結果，編列苗栗縣山坡地集水區調查規劃之分年分期計畫如表2。

表1 苗栗縣山坡地集水區治理需求級序及經營重點評估表
項次	子集水區編號	子集水區	現況調查評估				經營重點	治理 / 需求 / 級序
			優先處理 / (件)	需要處理 / (件)	暫緩處理 / (件)	合計 / (件)
1	0902001	景山溪	6	8	5	19	土砂災害防治	1
2	0801003	雞隆河	6	4	2	12	土砂災害防治	2
3	0701004	南港溪	6	2	3	11	土砂災害防治	3
4	0901026	大安溪中游	6	2	2	10	土砂災害防治	4
5	0801007	後龍溪下游	6	1	0	7	土砂災害防治	5
6	0701002	中港溪中游	5	1	1	7	土砂災害防治	6
7	3101004	通霄溪	4	6	5	15	土砂災害防治	7
8	3101005	苑裡	4	3	0	7	土砂災害防治	8
9	0801004	汶水溪	4	1	0	5	土砂災害防治	9
10	3101001	西湖溪	2	13	5	20	土砂災害防治	10
11	0801002	後龍溪上游	2	4	3	9	土砂災害防治	11
12	0801006	沙河溪	2	3	0	5	土砂災害防治	12
13	0801001	大湖溪	2	2	0	4	土砂災害防治	13
14	0801005	後龍溪中游	2	1	1	4	土砂災害防治	14
15	3101002	白沙屯	2	1	0	3	土砂災害防治	15
16	3101003	通霄	2	0	1	3	土砂災害防治	16
17	0701001	大東河	2	0	0	2	土砂災害防治	17
18	0802001	明德水庫	1	3	2	6	土砂災害防治	18
19	0901031	士林	1	2	0	3	土砂災害防治	19
20	0701003	坪潭	1	1	0	2	土砂災害防治	20
21	0701005	中港溪下游	1	0	0	1	土砂災害防治	21
22	0901004	北坑溪	0	1	0	1	區域性水土資源保育	22
23	0901024	司馬限山	0	1	0	1	區域性水土資源保育	23
24	0901032	麻必浩溪	0	1	0	1	區域性水土資源保育	24
25	0901023	天狗	0	0	0	0	農村發展	25
26	3002003	冷水坑	0	0	0	0	農村發展	26
27	0901016	雪見	0	0	0	0	農村發展	27
28	0901034	蘇魯	0	0	0	0	農村發展	28

資料來源：本計畫統計整理

表2 苗栗縣山坡地集水區調查規劃分年分期計畫
項次	集水區編號	子集水區	經營重點	治理需求 / 級序	分年分期 / 順序*	備註
1	0902001	景山溪	土砂災害防治	1	第1期	--
2	0801003	雞隆河	土砂災害防治	2	第1期	--
3	0701004	南港溪	土砂災害防治	3	--	99已規劃
4	0901026	大安溪中游	土砂災害防治	4	--	100已規劃
5	0801007	後龍溪下游	土砂災害防治	5	第1期	--
6	0701002	中港溪中游	土砂災害防治	6	--	99已規劃
7	3101004	通霄溪	土砂災害防治	7	第1期	--
8	3101005	苑裡	土砂災害防治	8	第2期	--
9	0801004	汶水溪	土砂災害防治	9	--	99已規劃
10	3101001	西湖溪	土砂災害防治	10	第2期	--
11	0801002	後龍溪上游	土砂災害防治	11	第2期	--
12	0801006	沙河溪	土砂災害防治	12	第2期	--
13	0801001	大湖溪	土砂災害防治	13	第3期	--
14	0801005	後龍溪中游	土砂災害防治	14	第3期	--
15	3101002	白沙屯	土砂災害防治	15	第3期	--
16	3101003	通霄	土砂災害防治	16	第3期	--
17	0701001	大東河	土砂災害防治	17	第4期	--
18	0802001	明德水庫	土砂災害防治	18	第4期	--
19	0901031	士林	土砂災害防治	19	第4期	--
20	0701003	坪潭	土砂災害防治	20	第4期	--
21	0701005	中港溪下游	土砂災害防治	21	--	99已規劃

*註：預定執行期程以每期為2~3年度辦理，實際執行期程仍須依照水土保持局臺中分局經費及需求辦理。
資料來源：本計畫統計整理

Abstract
The scope of this project comprises of slopeland within Miaoli County and an approximate area of 89,611 hectares. It primarily encompasses 28 sub-watersheds in the slopeland with watershed area totaled at 150,202 hectares. Due to frequent heavy rainfalls and time-lapse rainfall events in recent years, the disasters gradually tend to be compound in nature. Therefore in order to have a good command of the ensuing operation for all sub-watersheds within jurisdiction, we specifically proceeded to review and assess all slopeland watersheds within Miaoli County. In addition, we also planned the annual and phased-in investgations in the watersheds with the hope to reach multiple objectives in the disaster control, watersheds operations and conservations.

According to the 2001~2011 watershed investgation planning report, 22 items had been implemented and these can serve as the foundation background information for each sub-watershed. There are a total of 125 currently investigated disaster regions which can be broken down into 3 types of disasters with classes of top-priority, needed to process and on-hold. There are 202 items completed in the category of watershed remediation investigation. After they are assessed for functionalities and there are 169 Class-A, 30 Class-B and 3 Class-C with 33 damaged items.

The operation themes for watershed can be separated into three-staged objectives: “Safety, transition and sustainability” for the purpose of protecting the lives and property safeties for the protected subjects within the watershed. And the operation theme at the current phase is prioritized as “Safety”.

Under the pretext of “safety” operation, in order to control the management and remediation characteristics for each sub-watershed at slopeland within Miaoli County, and guided by investigate findings and the remediation requirements assessed as high-priority within watershed area, the operation will focus on “Sediment disaster prevention”. For those required remediation and put on-hold, the operation will focus on “Regional soil and water resources conservation”. For those currently without significant disaster remediation demand, they can provide and serve as the good watershed environment needed by rural village development. The essential for watershed operation rests at “Rural development”. And according to different operation focuses for sub-watersheds at each slopeland, these can serve as references intended for watershed operation personnel.

Findings from the appraisals indicate that, first of all, 21 sub-watersheds at Jing-Shan Creek, etc, they require top-priority remediation processing. The operation focus is “Sediment-disaster prevention” and the remediation and disaster prevention tasks for watershed should be implemented as such. Other than these, 3 sub-watersheds at Bei-Kun Creek, etc, they were appraised with the remediation requiring processing and on-hold. The operation focus should be “Regional soil and water resources conservation”. The management and remediation should strengthen the soil and water conservation at watershed as the theme. Lastly, 4 sub-watersheds at Tien-Goh, etc, their current statuses indicate less significant need for sediment disaster prevention and they can also provide good watershed environment needed by rural village development. The operation focus should be “Rural development” which demands the integration of water and soil conservation with rural rejuvenation so as to achieve the objective of water and soil resource sustainable operation at watershed.